ENGINEERING PROJECT PLAN

# Gesture-Controlled Drone

A two-year, from-parts quadcopter and ESP32 hand-tilt controller project

| Project parameter | Confirmed choice |
| --- | --- |
| Student level | Class 11 hobby robotics project |
| Schedule | 24 months |
| Maximum planned budget | ₹15,000 |
| Team | 3 students |
| Build approach | Assemble airframe and electronics from individual parts |
| Control | Hand tilt with ESP32 and motion sensor |
| Flight setting | Indoor first; controlled outdoor testing later |
| Tools | Soldering iron, multimeter and laptop available; no 3D printer |

DESIGN DECISION Build the drone from individual parts, but use a proven flight-controller board and established firmware for stabilization. The team still designs the gesture controller, wireless link, receiver interface, wiring, assembly, configuration and test process.

Prepared as a practical planning document. Prices, component availability and local aviation rules must be rechecked before purchasing and before outdoor flight.

# Document Guide

| Section | What it contains |
| --- | --- |
| 1-3 | Project brief, objectives, scope and success definition |
| 4-7 | Architecture, hardware, gesture control and communications |
| 8-10 | Flight-controller strategy, build method and software design |
| 11-13 | 24-month schedule, team roles and budget |
| 14-17 | Testing, safety, risk and documentation |
| 18-20 | Success criteria, future upgrades and appendices/checklists |

## How to use this plan

Treat each milestone as a gate. Do not proceed to the next flight-risk stage until the current gate passes.

Buy only the parts needed for the next stage. The final drone parts should be selected closer to assembly.

Keep a dated engineering log with photos, measurements, failures, fixes and test results.

All propeller-on tests require an experienced adult or robotics mentor, a clear test zone and a pre-flight checklist.

## Project at a glance

| Area | Baseline target |
| --- | --- |
| Aircraft | Small 2.5-3 inch guarded quadcopter, target mass below 250 g |
| Controller | Wearable or hand-held ESP32, MPU6050-class IMU, safety buttons, LED/buzzer |
| Link | ESP-NOW for prototype; range and packet-loss testing required |
| Flight mode | Angle/self-level mode for early testing |
| Commands | Roll, pitch, yaw, throttle, arm/pre-arm, take-off/land workflow, calibration and emergency action |
| Demonstration | Low-altitude controlled route with safe hover and landing |

# 1. Project Overview

The project will create a small quadcopter assembled from commercially available parts and a custom hand-tilt controller. An inertial measurement unit (IMU) detects the pilot's hand orientation. An ESP32 converts that motion into flight commands and transmits them to an ESP32-based receiver on the aircraft. A dedicated flight controller stabilizes the quadcopter and drives the electronic speed controllers (ESCs).

CORE PRINCIPLE Gestures request movement; the flight controller keeps the aircraft stable. The hand controller must never drive motors directly.

# 2. Objectives

Design a reliable gesture interface for roll, pitch, yaw and throttle.

Assemble a guarded quadcopter from compatible frame, motor, propeller, ESC, battery and flight-controller parts.

Build a short-range wireless control link with packet validation and communication-loss handling.

Demonstrate safe arming, low-altitude flight, hover, directional movement, rotation and landing.

Develop the system through measurable bench tests before any flight.

Produce a complete portfolio package: report, diagrams, code, data, video and presentation.

# 3. Scope and Boundaries

| Included | Not included in Version 1 |
| --- | --- |
| Airframe assembly and wiring | Designing stabilization firmware from first principles |
| Custom ESP32 gesture transmitter and receiver | Long-range, autonomous or beyond-visual-line-of-sight flight |
| All four flight axes and safety controls | Payload carrying, delivery or object lifting |
| Indoor tests and later calm-weather outdoor tests | Crowded-area, road, rooftop or high-altitude operation |
| Proven flight-controller firmware configuration | FPV camera/video transmitter |
| Test logs, report, presentation and demo video | Automatic navigation or GPS missions |

# 4. System Architecture

HAND MOTION  →  IMU  →  ESP32 TRANSMITTER  ⇢  WIRELESS LINK  ⇢  ESP32 RECEIVER  →  FLIGHT CONTROLLER  →  ESCs  →  MOTORS

| Subsystem | Main function | Key output |
| --- | --- | --- |
| Hand controller | Measures hand pitch/roll, reads buttons, applies filtering and safety logic | Validated control packet |
| Wireless link | Transfers control data and detects stale or missing packets | Fresh command or link-loss state |
| Drone receiver | Maps packet values to flight-controller channels | Roll, pitch, yaw, throttle and auxiliary channels |
| Flight controller | Stabilizes attitude, applies modes and failsafe | Motor demands |
| ESC and motors | Convert demands into propeller speed | Thrust and movement |
| Power system | Supplies safe regulated voltages | Battery power and 5 V/3.3 V rails |

## Data flow and safety flow

Read IMU and buttons at a fixed update rate.

Filter noise, apply neutral calibration, dead zone and output limits.

Create a packet with sequence number, controls, modes and safety state.

Receiver accepts only valid, recent packets.

If packets stop, receiver outputs an invalid/no-signal condition so the flight controller enters its configured failsafe.

Flight controller decides whether arming is allowed and stabilizes the drone.

## Interfaces to freeze before final purchasing

Flight-controller mounting pattern and frame space.

Motor size, KV rating, propeller size, battery cell count and ESC current rating.

Receiver signal method supported by the selected flight controller.

Available regulated power rail for the onboard ESP32, including voltage and current.

Total mass, centre of gravity and guarded-propeller clearance.

# 5. Hardware Design

## 5.1 Gesture controller

| Label | Qty. | Component | Baseline specification and integration note |
| --- | --- | --- | --- |
| G-01 | 1 | ESP32 development board | Main glove controller and ESP-NOW transmitter. Use a common USB-programmable board with accessible 3.3 V GPIO. |
| G-02 | 1 | 6-axis IMU module | MPU6050-class accelerometer/gyroscope module for pitch and roll sensing; confirm 3.3 V logic compatibility. |
| G-03 | 4 | Momentary push-buttons | Dedicated pre-arm/arm, mode, calibration, and land/emergency inputs. Use deliberate press/hold logic in software. |
| G-04 | 2-3 | Status LEDs | Separate power/link, mode, and warning indication where practical; choose clearly distinguishable colours. |
| G-05 | 2-3 | LED current-limiting resistors | Typically 220-330 ohm, one in series with each discrete LED. |
| G-06 | 1 | Active piezo buzzer | Audible connection, arming, calibration, low-battery, and fault feedback; select a 3.3 V-compatible type. |
| G-07 | 1 set | Buzzer driver parts | Small NPN transistor or logic MOSFET plus base/gate resistor and flyback protection if required by the selected buzzer. |
| G-08 | 1 | Protected 1-cell LiPo battery | Portable glove power; approximately 500-1000 mAh. Final capacity depends on enclosure size and measured run time. |
| G-09 | 1 | 1S LiPo charging/protection module | USB charging board with over-charge, over-discharge, and short-circuit protection appropriate to the selected cell. |
| G-10 | 1 | Voltage regulator/power module | Stable rail matched to the ESP32 board input. Confirm output voltage, peak current, efficiency, and dropout voltage. |
| G-11 | 1 | Master power switch | Accessible latching slide or rocker switch rated for the battery current. |
| G-12 | 1 set | Decoupling capacitors | 0.1 uF ceramic near modules plus 10-100 uF bulk capacitance near the ESP32 supply to reduce resets and noise. |
| G-13 | 1 | Solderable perfboard | Final controller interconnect after breadboard testing; size it to the enclosure and keep sensor wiring short. |
| G-14 | 1 set | Polarized connectors | JST-style battery and module connectors for safe removal and servicing; label power and signal plugs. |
| G-15 | 1 set | Flexible hookup wire | Stranded, colour-coded wire for power, I2C, buttons, LEDs, and buzzer; use a suitable small gauge. |
| G-16 | 1 | USB data cable | Programming, serial logging, and bench power. Verify that it carries data, not charge only. |
| G-17 | 1 | Glove or wrist strap | Comfortable adjustable base that holds the IMU in a repeatable orientation without restricting hand movement. |
| G-18 | 1 | Controller enclosure/baseplate | Small ABS project box or acrylic plate for the ESP32, battery, switch, and controls; no 3D printer required. |
| G-19 | 1 set | Mounting and insulation materials | Nylon standoffs, screws, heat-shrink, foam tape, hook-and-loop tape, cable ties, and strain relief. |
| G-20 | 1 set | Breadboard and jumper wires | Prototype-only items for IMU, button, LED, buzzer, and power tests before soldering the final controller. |

Glove procurement note: baseline parts are listed for planning; record the exact part number, seller, price, mass, voltage/current rating, connector type, and compatibility evidence before ordering.

## 5.2 Drone

| Label | Qty. | Component | Baseline specification and integration note |
| --- | --- | --- | --- |
| D-01 | 1 | Guarded quadcopter frame | 2.5-3 inch frame with replaceable propeller guards; verify motor holes, FC mounting pattern, battery space, and prop clearance. |
| D-02 | 1 | Flight controller + 4-in-1 ESC | F4-class or newer AIO board; approximately 20-35 A ESC. Confirm firmware target, receiver input, motor protocol, voltage range, and regulated outputs. |
| D-03 | 4 | Brushless motors | Matched set sized for the frame. Select KV only after fixing propeller diameter and battery cell count; buy one spare if budget permits. |
| D-04 | 3+ sets | Propellers | Correct diameter, pitch, shaft fit, and rotation for the selected motors/frame; include clockwise and counter-clockwise props plus spares. |
| D-05 | 1-2 | Flight LiPo battery | Cell count and capacity matched to motor/propeller data and ESC voltage; confirm discharge rating, connector, mass, and centre of gravity. |
| D-06 | 1 | LiPo balance charger | Charger specifically supporting the selected battery chemistry and cell count; use under supervision on a fire-resistant surface. |
| D-07 | 1 | ESP32 receiver board | Lightweight onboard ESP32 for ESP-NOW reception and command validation; confirm antenna clearance, mass, power, and mounting space. |
| D-08 | 1 | Receiver voltage regulator/BEC | Regulated supply matched to the ESP32 input with enough peak-current margin; bench-test for brownouts under motor load. |
| D-09 | 1 set | Receiver-to-FC interface parts | Signal wire/connector and any required inverter, level shifter, or protocol adapter after the flight-controller input method is confirmed. |
| D-10 | 1 | Low-ESR power capacitor | Voltage rating above maximum battery voltage; mount near the ESC battery input to reduce electrical noise and voltage spikes. |
| D-11 | 1 | Lost-model/status buzzer | Flight-controller-compatible buzzer for warnings and locating the aircraft; confirm voltage and driver requirements. |
| D-12 | 1 | Battery connector and pigtail | Connector type matched to the battery and current demand, with correctly gauged silicone wire and secure strain relief. |
| D-13 | 1 set | Silicone power and signal wire | Colour-coded wire sized for battery, motor, regulated power, UART/receiver, and buzzer connections. |
| D-14 | 1 set | Board connectors/headers | Low-mass polarized plugs or solder pads for the receiver, regulator, buzzer, and service connections; avoid loose Dupont plugs in flight. |
| D-15 | 1 set | Battery mounting parts | Hook-and-loop strap plus non-slip battery pad; the battery must not shift during manoeuvres or a minor impact. |
| D-16 | 1 set | FC mounting hardware | Correct-size nylon standoffs, soft grommets, nuts, and screws to fit the frame while controlling vibration. |
| D-17 | 1 set | Motor/frame fasteners | Correct screw diameter and length; screws must not touch motor windings. Include spares and thread-lock only where appropriate. |
| D-18 | 1 set | Replacement guards/frame parts | At least one set of the most crash-prone guard or arm parts if the chosen frame supports replacement sections. |
| D-19 | 1 set | Insulation and strain relief | Heat-shrink tubing, braided sleeve where useful, liquid electrical tape, and protection at sharp frame edges. |
| D-20 | 1 set | Cable-management materials | Small cable ties, cloth/electrical tape, and removable foam mounting tape; keep wiring clear of props and the FC sensors. |
| D-21 | 1 | Antenna retention mount | Non-conductive tube, tie, or bracket that keeps the ESP32 antenna clear of carbon, power wiring, and propellers. |
| D-22 | 1 | Temporary conventional RC receiver | Commissioning-only safety aid for first hover tests if a compatible transmitter can be borrowed; remove or retain as backup after validation. |
| D-23 | 1 | Smoke stopper/current limiter | Bench commissioning tool placed between battery and aircraft for first power-up; not carried during flight. |

Drone procurement note: baseline parts are listed for planning; record the exact part number, seller, price, mass, voltage/current rating, connector type, and compatibility evidence before ordering.

# 6. Component Selection Method

DO NOT ORDER THE FINAL POWERTRAIN YET Develop the two-ESP32 controller first. When buying flight parts, choose one compatible system rather than mixing attractive individual listings.

## Compatibility chain

| Decision | Must agree with |
| --- | --- |
| Propeller diameter | Frame guard clearance and motor capability |
| Motor size and KV | Propeller load, battery cell count, desired mass and ESC current |
| Battery | Motor voltage, ESC voltage, connector, charger and centre of gravity |
| ESC rating | Expected motor current plus safety margin |
| Flight controller | Frame mounting, receiver interface, firmware and power outputs |
| Receiver power | ESP32 input requirements and regulator capacity |

## Purchase gates

Gate A - Controller prototype: two ESP32 boards, IMU, buttons, LEDs/buzzer and breadboard.

Gate B - Bench receiver: signal-conversion parts only after the chosen flight-controller interface is confirmed.

Gate C - Airframe: purchase a matched frame, motors, flight controller/ESC, props, battery and charger set.

Gate D - Spares: buy extra props, connectors and one or two high-failure items only after the first build is understood.

## No-3D-printer mechanical approach

Use a commercially available guarded frame.

Mount the controller in a small ABS project box, acrylic plate or reinforced wrist strap.

Use nylon standoffs, hook-and-loop straps, heat-shrink, cable ties and foam tape where appropriate.

Keep all mounts removable so parts can be replaced after testing.

# 7. Gesture and Command Design

| Control state | Hand input | Command |
| --- | --- | --- |
| Horizontal mode | Tilt forward/back | Pitch forward/back |
| Horizontal mode | Tilt left/right | Roll left/right |
| Altitude/yaw mode (button held) | Tilt forward/back | Throttle up/down around a safe centre |
| Altitude/yaw mode (button held) | Tilt left/right | Yaw left/right |
| Any flight mode | Neutral hand | Centred roll/pitch/yaw; controlled throttle state |
| Ground only | Two-stage deliberate button sequence | Pre-arm then arm |
| Any state | Dedicated emergency action | Command safe landing/failsafe behavior as designed |

## 7.1 Signal processing

Calibrate: store the comfortable neutral hand orientation.

Filter: combine IMU measurements and smooth small hand tremors.

Apply dead zone: ignore small movement near neutral (initially about ±10°, then tune from data).

Map tilt: convert useful tilt range into limited channel output.

Rate limit: prevent sudden jumps when changing modes or moving the hand quickly.

Validate: reject impossible sensor values and require stable neutral before arming.

## Suggested first-pass thresholds

| Hand angle from neutral | Interpretation | Initial response |
| --- | --- | --- |
| Within ±10° | Neutral/dead zone | No roll or pitch demand |
| 10-20° | Small intentional tilt | Slow movement |
| 20-35° | Clear tilt | Moderate movement |
| Above 35° | Excessive tilt | Clamp at configured maximum |

These are starting values, not final specifications. The team must record real sensor data from all three users and tune thresholds to minimize false commands.

## Arming and landing logic

Arming is permitted only when the receiver is connected, throttle is safe, hand is neutral and the pre-arm condition is active.

Take-off should initially be a supervised throttle procedure, not a single gesture.

Landing should use a deliberate button or controlled throttle reduction. Automatic take-off/landing is a later enhancement.

An emergency control is not a substitute for correctly configured flight-controller failsafe.

# 8. Communication Method

ESP-NOW is suitable for the prototype because two ESP32 boards can communicate directly without a router. The team must still measure range, latency and packet loss in the actual build. Outdoor use should remain close and low until a more robust link or backup conventional controller is validated.

## Command packet

| Field | Purpose |
| --- | --- |
| Sequence number | Detect repeated or out-of-order packets |
| Timestamp/age | Reject stale commands |
| Roll, pitch, yaw, throttle | Four flight-control values |
| Mode | Horizontal or altitude/yaw mapping |
| Pre-arm and arm state | Deliberate motor-start logic |
| Calibration state | Neutral-setting request |
| Checksum/version | Detect corruption and incompatible packet formats |

## 8.1 Link-loss behavior

FAILSAFE REQUIREMENT If a valid packet is not received within the tested timeout, the receiver must stop presenting valid live control data. The flight controller must then enter its independently configured failsafe state.

Never keep replaying the last movement command after the link is lost.

Show link status on the hand controller and, where possible, on the drone.

Test packet timeout with propellers removed, then in a restrained/safe test setup, before any free flight.

Log packet rate, missed packets and maximum safe tested distance.

# 9. Flight-Controller Strategy

Use a dedicated multirotor flight controller running established firmware. It handles sensor fusion, motor mixing, self-level mode, receiver input, arming checks and failsafe. The team configures and documents it; the project does not attempt to recreate safety-critical stabilization code.

| Stage | Recommended approach |
| --- | --- |
| Receiver prototype | Begin with the simplest flight-controller-supported interface that can be tested safely |
| Early flight | Use a temporary conventional joystick controller and angle/self-level mode |
| Gesture integration | Replace joystick channel sources only after stable hover is achieved |
| Final interface | Prefer a supported serial receiver method if practical; treat PPM as a prototype/legacy option |

## Configuration checklist

Correct board target and current stable firmware selected.

Accelerometer orientation and calibration verified.

Receiver channels centred and moving in the correct direction.

Arm/pre-arm mapped to auxiliary controls and checked.

Motor order and direction verified with propellers removed.

Angle/self-level mode enabled for early flight.

Low-voltage warning and failsafe configured.

Final configuration exported and stored with the project files.

# 10. Software Design

| Transmitter modules | Responsibility |
| --- | --- |
| imu_reader | Read raw acceleration/gyro data and report sensor health |
| orientation_filter | Estimate pitch/roll and smooth noise |
| gesture_mapper | Apply calibration, dead zone, limits and two-mode mapping |
| safety_manager | Evaluate neutral, buttons, arming sequence and warnings |
| radio_sender | Build and transmit versioned command packets |
| status_output | Drive LEDs/buzzer and optional debug display |

| Receiver modules | Responsibility |
| --- | --- |
| radio_receiver | Accept packets and record packet age/sequence |
| packet_validator | Check format, values, sequence and freshness |
| channel_mapper | Convert normalized commands into supported receiver channels |
| failsafe_manager | Remove valid output on timeout and prevent unsafe arming |
| telemetry_logger | Report link and channel values during bench testing |

## Coding standards

Keep constants such as dead zones, maximum output and timeout in one configuration section.

Use meaningful names and short, single-purpose functions.

Store every tested firmware version in source control with a matching test log.

Include a bench-test mode that never enables arming.

Do not hide safety behavior inside gesture-mapping code.

# 11. Detailed 24-Month Timeline

| Months | Main work | Exit milestone |
| --- | --- | --- |
| 1-2 | Learn roll/pitch/yaw/throttle; define requirements; set up repository and logbook | Requirements and safety charter approved |
| 3-4 | Wire IMU; collect raw data; calculate stable hand orientation | Repeatable pitch/roll readings |
| 5-6 | Calibration, filtering, dead zones, button states and feedback | Five hand states detected reliably |
| 7-8 | ESP-NOW packet design, transmitter/receiver prototype and link indicators | Continuous validated packet stream |
| 9 | Timeout, stale-packet rejection and bench failsafe tests | Receiver enters safe state on link loss |
| 10-11 | Build temporary joystick input and channel-output prototype | Four channels move correctly on bench |
| 12 | Design review; final BOM, mass estimate and compatibility matrix | Purchase gate signed by team and mentor |
| 13-14 | Order parts; assemble frame, motors and electronics without propellers | Mechanically complete airframe |
| 15 | Flight-controller setup; receiver, modes, pre-arm and failsafe | All channels correct in configurator |
| 16 | Motor order/direction, power and vibration bench tests | Propeller-off acceptance checklist passed |
| 17 | Conventional-control low hover and basic movement | Stable 20-30 second hover |
| 18-19 | Introduce gesture roll/pitch with strict output limits | Safe horizontal gesture control |
| 20 | Add altitude/yaw mode and deliberate landing workflow | All four axes work individually |
| 21 | Integrated route, repeated indoor reliability tests | Planned route completed consistently |
| 22 | Calm-weather close outdoor tests; range and link-loss recheck | Outdoor test report completed |
| 23 | Reliability improvements, spares, final code freeze and video | Final demonstration rehearsal passed |
| 24 | Report, diagrams, presentation, budget reconciliation and portfolio packaging | Complete project package |

## 11.1 Monthly working rhythm

| Week | Team activity |
| --- | --- |
| 1 | Plan one measurable goal; check parts and safety constraints |
| 2 | Build or code the smallest testable change |
| 3 | Run tests, record data and diagnose failures |
| 4 | Improve, document, back up files and review the next gate |

## Milestone evidence

A milestone requires a dated video/photo, recorded values, pass/fail result and signed team review.

A software screen, import test or powered LED alone is not proof of an end-to-end flight function.

Flight milestones require repeatable performance, not one successful attempt.

# 12. Team Roles and Working Method

| Member | Primary responsibility | Secondary responsibility |
| --- | --- | --- |
| 1 - Airframe lead | Frame, motors, ESC, power wiring and mechanical inspection | Budget and inventory |
| 2 - Controls lead | ESP32, IMU, gesture processing and wireless packets | Test-data analysis |
| 3 - Integration lead | Flight-controller setup, receiver interface, test planning | Report, diagrams and presentation |

## Shared responsibilities

All three members attend propeller-on tests.

No member approves their own safety-critical change alone.

Roles rotate for short learning tasks so every member can explain the whole system.

Use issue cards with: task, owner, due date, test method and evidence link.

# 13. Estimated Budget

| Item | Planning allowance |
| --- | --- |
| Guarded 2.5-3 inch frame | ₹1,200 |
| Four brushless motors | ₹2,800 |
| AIO flight controller + 4-in-1 ESC | ₹3,500 |
| Propellers and spares | ₹400 |
| One flight battery | ₹1,100 |
| Balance charger | ₹1,500 |
| Two ESP32 boards | ₹800 |
| IMU sensor | ₹200 |
| Buttons, controller battery, strap/box | ₹700 |
| Buzzer, regulator, connectors and wire | ₹700 |
| Mounting/protection materials | ₹300 |
| Replacement reserve | ₹800 |
| Shipping/price contingency | ₹1,000 |
| TOTAL PLANNING LIMIT | ₹15,000 |

## 13.1 Budget controls

Record seller, date, exact part number, price, shipping, return policy and compatibility reason before ordering.

Keep at least ₹1,800 combined for replacement reserve and contingency.

Do not buy a camera, GPS or extra battery until the baseline drone flies safely.

Because the timeline is two years, re-price the final BOM at Month 12.

# 14. Testing and Validation Plan

| Level | Test focus | Pass evidence |
| --- | --- | --- |
| 1. Unit | IMU readings, buttons, LEDs, packet fields and channel mapping | Logged values within expected bounds |
| 2. Link | Packet rate, sequence, range, timeout and reconnection | No stale commands; known safe timeout |
| 3. Bench integration | Flight-controller channels, arming gates, motor order and direction | Configurator/video evidence; props removed |
| 4. Restrained/power | Voltage stability, regulator temperature, vibration and current behavior | No resets, overheating or loose connections |
| 5. Conventional flight | Hover and basic axes using joystick controls | Repeatable low hover and landing |
| 6. Gesture flight | One axis, then two modes, then full route | Repeated planned route within marked zone |
| 7. Reliability | Battery cycles, link-loss drills, multiple users and outdoor calm conditions | Test report with pass rate and failures |

## Key test cases

Neutral hand for 60 seconds: no unintended roll or pitch command.

Mode-button transition: channel outputs change smoothly, without a jump.

Controller power loss: receiver stops valid output and flight-controller failsafe activates.

IMU disconnect or invalid reading: arming is blocked.

Low battery: warning occurs early enough for a controlled landing.

Three users: calibration completes and basic gestures meet the accuracy target.

Twenty repeated indoor route trials: success rate and failure causes are recorded.

## Test record fields

Test ID • date/location • firmware/configuration version • hardware version • battery • objective • setup • steps • measured result • pass/fail • anomaly • corrective action • reviewer.

# 15. Safety Rules

NON-NEGOTIABLE Propellers stay removed during programming, receiver setup, motor-direction checks and most fault testing. Propeller-on tests require adult/mentor supervision.

## Battery and electrical safety

Use only a correct balance charger and charge on a fire-resistant surface under supervision.

Inspect the LiPo for swelling, puncture, heat or damaged wires before every use.

Never short the battery, leave it charging unattended or use a damaged pack.

Use strain relief, insulation and correctly rated connectors; check polarity before connection.

## Flight safety

Use propeller guards and eye protection for early tests.

Keep people, animals, roads, windows and fragile objects outside the test zone.

Fly low and close; never attach a payload.

Use a spotter and one designated pilot. Only the pilot gives commands.

Stop after any crash, unusual sound, vibration, hot component or unexplained movement.

For outdoor operation, recheck current Indian drone rules, permitted airspace and local restrictions at the time of testing.

# 16. Risk Assessment

| Risk | Likelihood / impact | Main controls |
| --- | --- | --- |
| Unexpected motor start | Medium / severe | Props-off setup; pre-arm + arm; neutral/throttle checks |
| Link loss or stale command | Medium / severe | Packet age/sequence; timeout; flight-controller failsafe |
| Gesture misclassification | Medium / high | Dead zone, filtering, output clamp, mode button, calibration |
| LiPo fire/damage | Low-medium / severe | Correct charger, inspection, supervision, fire-resistant area |
| Incompatible parts | Medium / high | Compatibility matrix, matched purchase, mentor review |
| Crash and prop damage | High / medium | Guards, low altitude, spares, clear zone |
| ESP32 brownout/reset | Medium / high | Regulated supply, bench load test, wiring separation |
| Schedule drift | Medium / medium | Monthly gates, small purchases, documented owners |
| Budget overrun | Medium / medium | Contingency, staged buying, no optional systems in V1 |
| Rule changes by 2028 | Medium / high | Recheck official rules and airspace before outdoor tests |

# 17. Documentation Deliverables

| Deliverable | Minimum content |
| --- | --- |
| Project report | Abstract, problem, objectives, design, methods, results, failures, conclusions and future work |
| Engineering drawings | Block diagram, wiring diagram, power diagram and component layout |
| Bill of materials | Exact part numbers, sellers, prices, dates and compatibility notes |
| Source code | Transmitter, receiver, configuration, README and version history |
| Flight-controller archive | Firmware target/version, configuration export and screenshots |
| Test package | Test plans, raw data, pass/fail records, photos and videos |
| Presentation | 8-12 slides covering need, system, build, tests, results, safety and learning |
| Demonstration script | Setup, safety announcement, calibration, flight route, landing and explanation |
| Portfolio page | Short summary, responsibilities, images, video, challenges and measurable results |

## Suggested folder structure

01_requirements
02_bom_and_budget
03_gesture_transmitter
04_drone_receiver
05_flight_controller
06_diagrams
07_test_data
08_photos_and_video
09_report_and_presentation

# 18. Success Criteria

| Criterion | Target |
| --- | --- |
| Gesture recognition | Neutral + four directional states detected reliably after calibration |
| Neutral stability | No unintended roll/pitch demand during a 60-second neutral-hand test |
| Arming safety | Cannot arm without connection, neutral/safe inputs and deliberate two-stage action |
| Communication | Packet-loss behavior and maximum tested range documented |
| Failsafe | Loss of valid commands activates the configured safe response |
| Conventional flight | Repeatable stable hover for at least 20-30 seconds |
| Gesture flight | All four axes work individually and in a planned route |
| Route demonstration | Take off, hover, rectangle, yaw turn and controlled landing |
| Reliability | At least 80% success across 20 final indoor route trials, with failures explained |
| Budget | Final spend at or below ₹15,000 or variance justified |
| Documentation | Complete code, diagrams, logs, report, presentation and video |

# 19. Future Enhancements

| Enhancement | Prerequisite |
| --- | --- |
| More robust radio / conventional backup transmitter | Baseline gesture system validated |
| Altitude hold or assisted take-off/landing | Reliable baseline flight and suitable sensors/firmware support |
| Small display on controller | Stable power and completed safety indicators |
| Improved IMU and sensor fusion | Recorded evidence that current sensor limits performance |
| Telemetry to laptop/phone | Secure, non-blocking link and clear user need |
| GPS-assisted outdoor functions | Rules, budget, mass, power and safety review |
| Custom PCB and enclosure | Circuit and connector design frozen after extensive prototyping |

UPGRADE RULE Add only one enhancement at a time, with a written test plan and rollback path. Optional features must not weaken the safety baseline.

# 20. Appendices and Checklists

## Appendix A - Final purchase checklist

☐ Exact frame, motor, propeller, ESC and battery combination checked

☐ Flight-controller mounting and receiver input confirmed

☐ ESP32 power regulator voltage/current confirmed

☐ Charger supports battery chemistry and cell count

☐ Expected current stays below ESC rating with margin

☐ Estimated all-up mass and centre of gravity recorded

☐ Spare propellers and required connectors included

☐ Seller, warranty/return policy and delivery time recorded

☐ Team and mentor approve the compatibility matrix

## Appendix B - Propeller-off bench checklist

☐ Frame screws tight; wires insulated and strain-relieved

☐ Correct polarity verified with multimeter

☐ Flight controller and ESP32 power rails stable

☐ Receiver channels centred and directions correct

☐ Arming blocked in unsafe conditions

☐ Motor order and rotation direction correct

☐ Link-loss and controller-power-loss tests pass

☐ Configuration and firmware versions backed up

## Appendix C - Pre-flight checklist

☐ Permission, adult/mentor and spotter present

☐ Test area clear; no people, animals, roads or fragile objects nearby

☐ Weather calm and outdoor rules/airspace checked, if applicable

☐ Frame, guards, motors and props undamaged and tight

☐ Battery undamaged, secured and adequately charged

☐ Correct firmware/configuration version loaded

☐ Controller calibrated; link indicator normal

☐ Pre-arm/arm, mode and emergency controls understood

☐ Planned maneuver and abort point stated aloud

☐ Camera/log ready; only designated pilot commands the drone

## Appendix D - Post-flight checklist

☐ Disarm, disconnect battery and allow components to cool

☐ Inspect props, guards, frame, motors, wires and battery

☐ Record flight time, battery condition and unusual behavior

☐ Save logs/video and name them with date and test ID

☐ Create corrective actions before the next flight

☐ Store battery safely at an appropriate storage state

## Appendix E - Design review questions

What evidence proves the current stage works end to end?

What single failure could cause the most harm, and how is it controlled?

Does the flight controller independently detect loss of valid control?

Can every wire, connector and power rail be explained by a team member?

Which assumption has not yet been tested?

What must pass before propellers may be installed?

Can the previous stable software/configuration be restored?

## Appendix F - Demonstration script outline

Introduce the problem, project objective and safety boundaries.

Show the system architecture and point out the flight controller's stabilization role.

Display neutral calibration and controller connection feedback.

Announce the flight path and clear the area.

Pre-arm, arm, take off, hover, complete the planned route and land.

Disarm and disconnect the battery.

Show test results, failures overcome, budget and future enhancements.

PROJECT MOTTO Build slowly. Test one layer at a time. Record evidence. Fly only when the safety gate passes.